BEEP CAREER PLATFORM

Comprehensive Knowledge Base & Operating Document

Source: ChatGPT Conversation Export (432 Pages) — Full Coverage

EventBeep Technologies Pvt. Ltd.

# TABLE OF CONTENTS

- 1. Company Overview & Vision

- 2. Core Verticals & Business Models

- 3. Features & Product Capabilities

- 4. Differentiators & Moats

- 5. Target Demographics & Positioning

- 6. Core Team & Leadership

- 7. Departmental Structure (9 Departments)

- 8. Co-Founder Responsibility Matrix (Macro + Micro)

- 9. Execution Cadence & Cross-Function Rituals

- 10. Revenue Targets & Projections (FY25-26)

- 11. P&L Analysis & Vertical-wise Financial Health

- 12. Key Issues Identified & Strategic Action Plans

- 13. June 2025 Monthly Objectives by Vertical

- 14. Product Ownership & June Deliverables

- 15. UI/UX Career Program — Full 16-Week Curriculum

- 16. UI/UX Program Session Types & Learning Formats

- 17. UI/UX Program Milestones & Submissions (Revised)

- 18. Program Automation & Quality Systems

- 19. Student Progress Tracking & Batch Management

- 20. Program Setup Checklist (Team Execution)

- 21. Program Outcomes & Skill Benchmarks

- 22. Team Touchpoints & Cadence Table

- 23. Beep Learn One-Pager & Co-Founder Role

- 24. CEO Operating System & Vertical North Stars

- 25. Meeting Cadence & Execution Rituals

- 26. Incentives, Motivation & Performance System

- 27. December 2025 — Full 360-Degree Review

- 28. All Issues & Concerns from December Meetings

- 29. Financial Statement Review (FY24-25)

- 30. Founder's Office — Role & Structure

- 31. Founder Alignment Meeting Structure

- 32. Accelerator Master Prompt & Form Responses

- 33. 2026 Goals, OKRs & Strategic Direction

- 34. Growth & Acquisition Plan to 10M Users

- 35. International Expansion Plan

- 36. Impact Metrics & Placement Targets (FY26)

- 37. Company Vision & Positioning Statement

- 38. AI COO System Prompt (Full)

- 39. Competitive Landscape

- 40. Key Metrics Reference & Recognition

# 1. Company Overview & Vision

Company: Beep (formerly EventBeep) — EventBeep Technologies Pvt. Ltd.

Sector: CareerTech + EdTech + HRTech

Headquarters: India (Global expansion pilots: UAE, SEA, US, UK)

Founded by: Saurabh Mangrulkar (CEO), Rakhi Pal (COO), Yogesh Nogia (CTO)

Vision Statement: Build the 'Tier-1 career system' for everyone — a global, AI-powered career OS that helps any student explore, upskill, and get hired fast, regardless of college, background, or country.

Beep is building the LinkedIn + Coursera for college students, focused on democratizing access to opportunities for Tier 2 and Tier 3 colleges in India. The vision is to create a mobile-first, gamified, AI-powered ecosystem that helps students Explore career paths, Learn through upskilling, and Earn via internships and jobs — replicating the experience of Tier 1 colleges for underserved students.

## 1.1 The Big Idea

Right now, Tier-1 colleges have a system: peers + culture + confidence, placements + alumni + recruiters, structured projects + mentorship, brand + signal. Beep's mission is to productize that system and deliver it to the masses — first in India (Tier 2/3), then globally (US international students, Middle East, SEA).

## 1.2 Vision in 3 Pillars

Career OS (for students): A daily-use app that guides students with AI roadmap + tasks, skills + projects + portfolio, mock interviews + feedback, community + mentors, 'one-click apply' opportunities.

Outcomes Engine: Beep isn't 'content' or 'job listings.' Beep is measured by outcomes: internships, jobs, salary improvement, confidence, skills proof.

Ecosystem Platform: Colleges use UniBeep to run placements. Recruiters use BeepHire to shortlist + interview + hire fast. Students feed the pipeline, outcomes strengthen trust, trust increases adoption — flywheel.

## 1.3 Core Flywheel

Beep App (B2C student OS) + Beep Learn (job-ready upskilling) + BeepHire (AI recruiter SaaS) + UniBeep (college placement SaaS) operating as a B2C/B2B/B2B2C flywheel. The four verticals are interconnected — student data powers recruiter matching, college partnerships drive distribution, learning completion signals drive hiring confidence.

## 1.4 AI-Native Positioning

As AI reduces entry-level roles and raises the bar on job readiness, students will need better proof-of-skill (projects, portfolios), better communication + problem-solving, faster iteration and specialization, and premium guidance and mentorship. Beep is positioned as the AI-native platform that addresses this shift with AI career roadmaps, AI mock interviews, AI resume scoring, shortlist predictors, and prompt-based design tools.

# 2. Core Verticals & Business Models

| Vertical | Business Model | Key Features | Revenue Target |
| --- | --- | --- | --- |
| 1. Recruiters Platform (B2B) — BeepHire | SaaS + Subscription for recruiter access to candidates, hiring analytics, shortlisting tools | AI-powered recruiter dashboard, candidate behavior analytics, WhatsApp hiring bot, auto-interview workflows, resume insights | Rs 30-50L MRR (Nov-Dec 2025) |
| 2. College Partnerships (B2B SaaS) — UniBeep | Paid dashboards for colleges to manage career services, placements, student performance tracking | Placement tools, resume parsing, recruiter connect modules, TPO panel, events management | Early-stage; 2 paid colleges; target 20-25 cumulative |
| 3. Courses (B2C) — Beep Learn | Mixed pricing: High-ticket (Rs 10K-30K), Micro-courses (Rs 399-999), Certifications (Rs 98-298) | Mentor-led modules, recorded content, certification, resume projects, AI tutors, capstone projects | Rs 1Cr/month by Sep-Oct 2025 |
| 4. Pro Plan Subscription (B2C) — Beep App | Rs 99/month; Premium plan with bundled tools, events, mentorship, recruiter visibility | AI career planner, mock interviews, Beep Bytes, internship priority, WhatsApp community, streaks | Rs 2L+ MRR now; goal: 5K+ conversions/mo |
| 5. Events & Playbooks (B2C/B2B) | Workshops, recorded sessions, career events via tickets, partner promotions | Mentor talks, corporate events, power communities, challenge-based learning | Ancillary revenue |

## 2.1 Revenue Model Detail

Beep Learn: High-ticket programs (Rs 10K-30K) are the primary revenue driver at ~48% of projected FY revenue. Micro-courses (Rs 399-999) and certifications (Rs 98-298) serve as entry points with upsell paths.

BeepHire: Recruiter SaaS subscriptions starting ~Rs 6,800/month per recruiter. Success fee model for placements. AI interview tools as add-on.

UniBeep: Annual college dashboard contracts (Rs 5-10L ACV per college). Placement operations + outcome playbooks.

Beep App Pro: Rs 99/month or Rs 499/year subscription. Web LP + App paywall. US bundle test at $49.

# 3. Features & Product Capabilities

## 3.1 Student Side (B2C)

- AI Career Planner: Auto-generated roadmap after resume upload and Q&A — personalized weekly/daily tasks

- Mock Interview + Scorecard: AI assesses speaking and answers with rubric-based scoring

- Internship/Job Tracker: Smart shortlisting predictor, real-time application status, 1-tap apply

- Beep Bytes: Reels-style short career videos for quick learning and engagement

- Course Hub: Certified programs, micro-degrees, projects with mentor-led and AI-guided modules

- College Communities: Gamified, region-based and open community modules with XP and leaderboards

- Pro Plan: Enhanced access to tools, community, mentors, job visibility, priority internship access

- Student Connect: Tinder-style social match for mentorship, networking, peer learning

- Career Tracker: Daily tasks, streaks, leaderboard, badges driving retention and engagement

- Resume Builder: AI-powered resume creation with ATS optimization and keyword suggestions

- Portfolio Builder: Guided portfolio creation for Notion/Webflow with templates

## 3.2 Recruiter Side (B2B)

- WhatsApp Hiring Bot: Automates engagement, screening, and shortlisting via conversational AI

- Scraping & Auto Outreach Engine: Sourcing passive candidates from LinkedIn, Naukri, and other platforms

- Auto Interviewing Engine: Conversational AI for interview rounds with scoring and transcripts

- Smart Filters: Tag-based filtering (courses done, colleges, engagement level, skill scores)

- Behavioral Insights: Tracks activity, login frequency, content engagement for candidate scoring

- Recruiter Dashboard: Post jobs, shortlist candidates, get AI interview reports, candidate analytics

- Talent Pool System: Curated pools of pre-screened candidates by role/skill/location

- 3-Hour Shortlist Promise: Pilot program for rapid candidate delivery on repetitive roles

## 3.3 College Side (B2B SaaS)

- TPO Dashboard: Manage placements, events, student engagement, recruiter integrations, reports

- Placement Reporting: Download-ready reports for management and accreditation

- Student Activity Monitor: Track student engagement, course completion, job applications

- Recruiter Visibility Engine: Connect colleges directly with hiring companies

- Bulk Upload: Partner college onboarding with batch student imports

- Event Management: Career drives, webinars, workshops scheduling and tracking

## 3.4 Full Product Lines

| Product Line | Target Audience | Description/Features |
| --- | --- | --- |
| Beep Student App | Students (Tier 2-3) | AI career planner, internships/jobs, Beep Bytes, courses, roadmap, resume tools, gamification, streaks, leaderboards |
| BeepHire | Recruiters/HR | Post jobs, shortlist candidates, AI interview reports, candidate analytics, dashboard, WhatsApp bot, talent pools |
| Beep College Dashboard | Colleges (TPOs) | Manage placements, events, student engagement, recruiter integrations, reports, bulk uploads |
| Micro & Flagship Courses | Students | Pre-recorded & mentor-led skill programs with projects, certification, upsell paths, AI tutors |
| Certification Engine | Students | Low-cost (Rs 98-298) assessments with verified skill validation and digital certificates |
| AI Career Tools Suite | Students | Resume scanner, shortlist predictor, mock interview AI, career roadmap AI, portfolio builder |
| WhatsApp Bot + Support | Students & Recruiters | Chat-led onboarding, job matching, support, nudges, retention flows |
| Beep Global Pilot | Intl. Students | Early-stage experiments in UAE, SEA, Africa with localized pricing & career tools |

# 4. Differentiators & Moats

| Moat | Description |
| --- | --- |
| Exclusive College Partnerships | Long-term tie-ups with 800+ colleges make it harder for competitors to enter; MoU-driven cadence |
| Gamified Community Engine | Sticky engagement via points, streaks, power communities, social recognition, XP ladders, season passes |
| AI-led Career Tools | Career roadmap generator, shortlist predictor, mock interview scoring, resume/portfolio AI, AI tutors |
| B2B + B2C Stack | Combines college SaaS, recruiter tools, and student products in one ecosystem — closed loop |
| Built-from-Scratch Infrastructure | 95% of tech stack is custom-built; highly optimized for student engagement and behavioral signals |
| Referral Flywheels | Viral growth via in-app referrals, friend invites, community exclusivity, campus ambassador network |
| Data & Distribution | 4M+ candidate profiles with engagement signals; deep Tier-2/3 penetration; high-engagement community |
| Signal Graph | AI-generated, mentor-verified artifacts (projects, reports, interview clips) — richer than certificates |
| Multi-sided Network | Students + colleges + recruiters + EdTech partners in one loop creating compounding retention |
| Brand & Social Proof | Shark Tank India, GSEA, CM Maharashtra Award, Google Appscale, NUMA, major media coverage |

## 4.1 Competitive Positioning

| Competitor Category | Players | Beep's Edge |
| --- | --- | --- |
| Job Boards | LinkedIn, Naukri, Apna | Focus on early-career, portfolio signals, time-to-shortlist, community-driven |
| EdTech/Courses | Scaler, PW, Internshala Trainings | Program + placement integration and recruiter access; not just courses |
| Campus Hiring | Handshake (global) | India-focused with deep Tier 2/3 penetration; affordable pricing |
| Recruiting/AI | GetWork.ai, Intervue | Differentiated via student pipeline + learning + explainable ranking |
| Career Prep | PrepInsta, Unstop | Win on program + placement integration; outcome-tied, not content-only |
| Networking | Peerlist | Community + learning + hiring unified; not just networking |

# 5. Target Demographics & Positioning

| Target Group | Description | Market Context |
| --- | --- | --- |
| Students | 18-25 year-olds, mostly Tier 2/3 Indian colleges. Seeking jobs, internships, mentorship, learning. | India has 40M+ college students; vast majority in Tier 2/3 with poor career access |
| Recruiters | Startups, SMEs, large companies hiring interns/freshers at scale with verified skill signals. | Hiring interns/freshers is slow and noisy; low signal, high ops workload |
| Colleges | Institutions seeking digital transformation in placements via dashboards and engagement tools. | TPOs lack modern tools; accreditation pressure drives digital adoption |
| International Students | UAE/US/UK students with visa uncertainty needing fast, credible career outcomes. | Strong willingness to pay; international-student inflow + competition rising |

## 5.1 Market Size & Why Now

The global entry-level talent market is fundamentally broken. AI is compressing hiring cycles and raising the bar on job readiness. Talent selection is shifting from 'resume keyword matching' to signal-based hiring (skills, projects, proof-of-work, behavior, fit). Students are increasingly willing to pay for premium outcomes: job-ready programs, mentorship, AI tutors, and faster hiring access.

India alone has 40M+ college students, with the vast majority in Tier 2 and Tier 3 institutions that lack structured career ecosystems. The Indian EdTech + HRTech market is projected at $30B+ by 2030. Beep targets the intersection of career services, upskilling, and hiring — a combined addressable market of $10B+ in India alone.

# 6. Core Team & Leadership

| Name | Role | Background / Details |
| --- | --- | --- |
| Saurabh Mangrulkar | Co-founder & CEO | Strategic leadership, growth, product, investor relations. Ex-Shark Tank India. Leads revenue, capital, brand, overall scale. Diploma + Mechanical Eng. Founder since teenage years. |
| Rakhi Pal | Co-founder & COO | Heads operations, partnerships, recruiter & college B2B, community. Empathetic leader, extremely hard working, passionate. Ex-founder MentorBoxx. Runs people really well. |
| Yogesh Nogia | Co-founder & CTO | IIT Delhi, ex-Dell. Leads technology, product development, AI/ML, UX/UI. Aesthetic sense, full-stack execution, visionary product design, idea-to-build speed. |
| Rudresh Yadav | Head of Sales & Strategy | Leads sales org and recruiter partnerships, instrumental in monetization. |
| Snehal Kamble | Senior Product Manager | Works on Beep Recruiter tools, roadmap execution, student experience. |
| Ritika Patwa | Community Lead (Student) | Drives student engagement, gamification, regional community growth. |
| Aniket | TPO Partnerships | Handles college-side integrations, lead generation funnels, onboarding. UniBeep vertical. |
| Aadesh | Performance Marketing Head | Manages ad campaigns, influencer collabs, budget-led user acquisition across Meta/Google/UAC. |
| Rohit | Consultant (Recruiters GTM) | Scale recruiter-side monetization and automation. Recently onboarded. |
| Diwakar | Beep Learn Operations | Owns course delivery, mentor management, sales for learning vertical. |
| Pooja | Beep Learn Support | Supports Diwakar on program operations and quality. |
| Nimisha/Shibili | Product Support | Product support across App, BeepHire, UniBeep verticals. |
| Donna | BeepHire Sales Ops | Sales operations support for recruiter vertical. |

# 7. Departmental Structure (9 Departments)

## 7.1 Growth & Marketing (Saurabh)

Sub-Functions: Paid Acquisition (Meta, Google, UAC, influencer); Content & SEO (YouTube, Reels, Blogs, Shorts); Referral Flywheels & Ambassadors; Conversion Funnels (CRO); Analytics & Growth Ops

KPIs: CAC < Rs 20, 1M+ MAU, 10% MoM growth, 3M+ reach/month

## 7.2 Revenue & Monetization (Saurabh)

Sub-Functions: Courses (Micro, Flagship, Certification); Pro Plan Subscriptions; Workshops, Services, Playbooks; Upsell Journeys & Pricing

KPIs: Rs 12 Cr/month revenue, LTV > Rs 400/user, >30% conversion

## 7.3 Recruiter B2B & College SaaS (Rakhi)

Sub-Functions: Recruiter Pipeline & Closures; College TPO SaaS Sales; Onboarding & Account Management; Recruiter Events & Success

KPIs: Rs 2-3 Cr/month from Recruiters + Colleges, 90-day NRR > 1.2

## 7.4 Product & Tech (Yogesh)

Sub-Functions: Mobile App (B2C): roadmap, AI tools, personalization; BeepHire Platform (B2B); College Dashboard (SaaS); AI/ML Stack; Infrastructure, CI/CD, Data Warehouse

KPIs: Feature velocity, NPS > 60, Bug SLA < 24h, Uptime 99.9%

## 7.5 Learning & Content (Saurabh + Lead)

Sub-Functions: Course Creation & Licensing; Beep Bytes; Content QA & Curriculum Design; Mentor Onboarding

KPIs: 50+ new micro-courses/quarter, 90% course NPS

## 7.6 Community & User Success (Rakhi)

Sub-Functions: Student Community Ops; Ambassador Program; Support (WA, Helpdesk, Retention); Streaks, XP, Gamification

KPIs: DAU/MAU > 30%, Pro Plan churn < 10%

## 7.7 Finance, Legal & Admin (Saurabh)

Sub-Functions: Budgeting, Forecasting; Cash Flow & MIS; Compliance, Legal; Vendor Management

KPIs: Burn < Rs 15L/month, runway > 12 months, collections > 90%

## 7.8 People & Culture (Rakhi)

Sub-Functions: Hiring & Onboarding; Performance Reviews & OKRs; Training & Upskilling; Culture, Wellness

KPIs: Hiring SLA < 30 days, 80%+ team eNPS, retention > 85%

## 7.9 Data & RevOps (To Build)

Sub-Functions: Pipeline management, dashboards, pacing models, pricing, attribution, single source of truth

KPIs: Daily automated CEO dashboard, real-time vertical pacing

# 8. Co-Founder Responsibility Matrix

## 8.1 Saurabh Mangrulkar — CEO

Macro: Growth Strategy, Revenue (all verticals), Investor Relations, Systems & Processes, Brand, Finance

### Micro-Level Detail

- Growth & Marketing: Final budget allocation for Meta/Google/UAC/influencers, Campaign performance analysis with Aadesh, Content performance reviews (Instagram, LinkedIn, YouTube), Weekly acquisition reviews (installs, CPI, signups, Pro trials)

- Revenue: Design and test pricing for Pro Plan (Rs 99/month, trials), Micro-courses (Rs 399-999), Flagship programs (Rs 10K-30K), Certifications (Rs 98-298), Monthly revenue pacing + projections, Funnel optimization landing to conversion, Collaborate with Product for upsell nudges

- Finance: MIS dashboard finalization, Revenue forecasting (3/6/12-month models), Fundraise materials + investor meetings, Cash burn + unit economics + margin targets

- Strategic: International Pilot (UAE, SEA, Africa), Viral engine design (WhatsApp invites, AI report virality), SEO + YouTube + UGC engine, Pro Plan value ladder strategy

## 8.2 Rakhi Pal — COO

Macro: Recruiter & College B2B, People & Hiring, Community, Internal Culture, Account Management

### Micro-Level Detail

- Recruiter Sales: Weekly CRM and pipeline review, SDR team hiring/scripts/demos/closures, Recruiter onboarding journey & success metrics, MoU & pricing negotiation with colleges, Cross-sell to existing recruiter database

- Community: Weekly WA support + onboarding checks, Power-user management and campus leads, XP leaderboard campaigns & reward system, Planning live events, mentor sessions, orientation days

- People: Hiring & onboarding with Finance & CEO, Intern & full-time JD finalization, Performance review system (monthly/quarterly), Culture building: check-ins, off-sites, rituals, feedback loops

- Retention: Gamification initiatives, Pro Plan community nudge & churn watch, Support satisfaction scoring (WA TAT, retention nudges)

## 8.3 Yogesh — CTO & CPO

Macro: Product Execution, Tech & Infra, UX/UI, AI/ML Engine, Engineering Team

### Micro-Level Detail

- Mobile App: Resume to AI Roadmap to Career Tracker to Action Plans, Home redesign for personalization, Tasks/streaks/leaderboard execution, Beep Bytes & content delivery

- BeepHire: JD to Application tracking to AI report to Shortlist cycle, Recruiter dashboard filters/reports/usage nudges, Admin tools for internal team efficiency

- College: TPO panel, placement report download, Events/student activity monitor/recruiter visibility

- AI: Career Roadmap GPT/LLM integration, Mock Interview scoring engine, Shortlist predictor via behavioral & resume vector embeddings, WhatsApp automation

- Infra: Server scaling, bug resolution TAT, CI/CD for Android builds, Product analytics (Mixpanel, Segment, Firebase), Engineering hiring & mentorship

# 9. Execution Cadence & Cross-Function Rituals

| Ritual | Cadence | Owner | Purpose |
| --- | --- | --- | --- |
| Founders Sync | Twice/week (Mon + Thu) | Saurabh | Align vision, catch issues early, unblock, prioritize |
| Weekly Dept Review | Weekly | Each Founder | Track metrics, unblock, iterate per department |
| B2B Sales Review | Weekly | Rakhi | Recruiter pipeline, college demos, closure status |
| Product Standup | Weekly | Yogesh | Tech sprint update, bug triage, velocity tracking |
| Revenue & Marketing Review | Weekly | Saurabh | Review CAC, CPIs, Pro plan, course funnel performance |
| OKR Planning & Retro | Monthly | All Leads | Track execution vs goals, re-forecast |
| Finance Review | Fortnightly | Saurabh | Track cash flow, targets, revenue health |
| All-Hands (Team) | Monthly | Rakhi | Culture + Direction + Spotlight wins |
| Revenue War-Room | Daily 9:30 AM | CEO + GMs | Review MTD pacing, pick 3 moves for next 24h |

## 9.1 Specialist Roles to Add

| Role | Why Now |
| --- | --- |
| Revenue Ops Analyst | Tie ad spend to funnel to revenue in real-time |
| Lead PM (B2C) | Drive execution of AI tools, onboarding wow, home UI |
| Inside Sales Head | Maximize recruiter B2B and college conversion |
| Community Growth Lead | Viral loop via students + WhatsApp activation |
| Data Analyst (BI) | Automate cohort analysis, churn heatmaps, campaign ROI |

# 10. Revenue Targets & Projections (FY25-26)

## 10.1 Monthly Revenue Ladder (Rs Lakhs)

| Month | Recruiters | Colleges | Certs | Micro | Flagship | Pro | Other | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| May '25 | 1 | 2 | 1 | 0.5 | 35 | 2 | 0.5 | 42 |
| Jun '25 | 2 | 3 | 2 | 1 | 40 | 2.5 | 0.5 | 51 |
| Jul '25 | 3 | 5 | 3 | 2 | 48 | 3 | 0.5 | 64.5 |
| Aug '25 | 5 | 7 | 5 | 4 | 60 | 4 | 1 | 86 |
| Sep '25 | 10 | 10 | 8 | 8 | 75 | 5 | 1 | 117 |
| Oct '25 | 20 | 12 | 15 | 15 | 85 | 6 | 1 | 154 |
| Nov '25 | 30 | 15 | 20 | 20 | 90 | 8 | 2 | 185 |
| Dec '25 | 40 | 20 | 25 | 25 | 95 | 10 | 2 | 217 |
| Jan '26 | 50 | 25 | 28 | 28 | 100 | 11 | 2 | 244 |
| Feb '26 | 60 | 30 | 32 | 30 | 105 | 12 | 2 | 271 |
| Mar '26 | 75 | 35 | 35 | 32 | 110 | 12 | 2 | 301 |

## 10.2 Quarterly Roll-ups

| Quarter | Months | Rs Lakhs | Rs Crore | Top Drivers |
| --- | --- | --- | --- | --- |
| Q1 | May+Jun+Jul | 157.5 | 1.575 | Flagship courses (Rs 123.5L), Recruiter (Rs 6L), Pro (Rs 7.5L) |
| Q2 | Aug+Sep+Oct | 357 | 3.57 | Flagship (Rs 220L), Micro (Rs 27L), Recruiter (Rs 35L) |
| Q3 | Nov+Dec+Jan | 646 | 6.46 | High-ticket (Rs 285L), Recruiter (Rs 95L), Pro (Rs 29L) |
| Q4 | Feb+Mar+Apr | 904 | 9.04 | Recruiter (Rs 225L), Micro+Flagship (Rs 182L), Certs (Rs 105L) |
| FY Total | Full Year | 2,064.5 | 20.6 | Crosses Rs 20.6 Cr; strong Q4 from B2B ramp |

## 10.3 Stream-wise Yearly Breakdown

| Revenue Stream | Total FY25-26 (Rs L) | % Contribution |
| --- | --- | --- |
| Recruiters SaaS | 366 | 17.7% |
| College Dashboard | 194 | 9.4% |
| Certifications | 237 | 11.5% |
| Micro-Courses | 195.5 | 9.5% |
| Flagship Courses | 993 | 48.1% |
| Pro Plan | 88.5 | 4.3% |
| Other | 20 | 1% |
| TOTAL | 2,064.5 | 100% |

Derivation: Base-rates from Funnel Strategy slides, compounded at month-on-month acceleration from phase road-maps. Front-loads high-ticket programmes (Flagship Courses) to secure cash-flow early; Recruiter & College SaaS ramp in H2 as ambassador blitz and placement-cell integrations kick in. 'Other' = brand campaigns & API fees. Growth rate: ~14% month-on-month.

# 11. P&L Analysis & Financial Health

## 11.1 Summary

| Metric | Value |
| --- | --- |
| Total Revenue | Rs 38,85,351 |
| Actual Revenue (Net of GST) | Rs 32,92,670 |
| Total Expenses | Rs 69,68,628 |
| Gross Profit | Rs -10,34,521 (-31% GM%) |
| Net Profit/Loss | Rs -36,75,958 (-112% NM%) |

## 11.2 Vertical-wise P&L

| Vertical | Revenue | Expenses | Net P/L | Margin |
| --- | --- | --- | --- | --- |
| Beep Learn | Rs 31,16,527 | Rs 36,16,132 | Rs -4,99,605 | -16% |
| BeepHire | Rs 38,499 | Rs 13,50,198 | Rs -13,11,699 | -3407% |
| UniBeep | Rs 38,136 | Rs 7,81,910 | Rs -7,43,774 | -1950% |
| Beep App | Rs 99,509 | Rs 12,20,388 | Rs -11,20,879 | -1126% |

## 11.3 Expense Breakdown

| Expense Type | Amount (Rs) | % of Revenue | Key Detail |
| --- | --- | --- | --- |
| Core Salaries | 17.22L | 52% | Nearly 44% of Net Revenue; needs benchmarking |
| Tech Tools + Infra | 11.57L | 35% | Mixpanel, Mongo, OpenAI, Leonardo, Paddle — audit usage |
| Meta Ads + Marketing | 12.49L | 38% | Rs 12.01L Meta Ads alone; low ROI on Beep App |
| Mentor Fees | 3.81L | 12% | Retain only high-ROI mentors |
| Business Consultant | 2.25L | 7% | Renegotiate or cut |
| Communications (Gupshup etc) | 2.5L | 8% | Gupshup, WebinarJam, Twilio, Exotel |
| Operations & Admin | 3.86L | 12% | Standard ops overhead |
| General (Rent, Utilities) | 3.89L | 12% | Fixed costs |
| Total Indirect | 26.41L | 80% | Extremely high ratio to revenue |

## 11.4 Key Issues Identified

| Issue | Impact | Recommendation |
| --- | --- | --- |
| High burn in BeepHire, TPO & App | -90%+ Net Margins | Tie ad spend to ROI, pause channels until monetization scales |
| Core Salaries exceed range | 52% of net revenue | Link salary payouts to vertical performance or cap |
| Overlapping tools | Rs 11.5L+ on tools | Rationalize unused/overused software tools |
| Meta Ads poor ROI on App | Rs 12L spent, <Rs 1.2L rev | Reassess targeting, creatives, or scale back App marketing |
| No volume revenue from Recruiter SaaS | Rs 38K Rev vs Rs 13.5L spend | Restructure B2B funnel; reduce overheads, make lean pilot |

# 12. Strategic Action Plans

## 12.1 Cost Review & Cuts (72-Hour Priority)

| Category | Action | Owner |
| --- | --- | --- |
| Tool Audit (Rs 11.5L+) | Review Mixpanel, Leonardo AI, Paddle.net, WebinarJam, OpenAI tokens — cancel/defer | Yogesh |
| Meta Ads (Rs 12L) | Pause low-converting App campaigns (ROI < 1.5x). Run only for proven Beep Learn funnels | Saurabh + Aadesh |
| Consultants | Re-evaluate Business Consultant (Rs 2.25L) & Mentor Fees (Rs 3.81L). Retain only high-ROI | Saurabh + Rakhi |
| College & Recruiter Spend | Freeze spending on TPO & Recruiter unless revenue-generating | Rakhi |
| Salary Review | Review core salaries vs output (Rs 17L+). Freeze hikes & new full-time unless proven ROI | Saurabh + Rakhi |

## 12.2 Revenue Acceleration (This Week)

| Action | Owner | Target |
| --- | --- | --- |
| Re-launch Beep Learn flagship funnel | Saurabh | Rs 10L/month by reactivating pipeline |
| Bundle Certifications + Pro Plan | Saurabh + PM | Rs 98 + Rs 99 model with WA onboarding |
| Flash sale for courses (Rs 499/999) | Growth + Content | Drive urgency via email & WA retargeting |
| Resume -> Roadmap -> Course funnel push | Yogesh + PM | Show relevant paid modules in roadmap |
| Personalize home screen upgrade options | Yogesh | Show CTA for trial-to-paid Pro Plan |

## 12.3 7-Day Game Plan

| Day | Action Focus |
| --- | --- |
| Day 1 | Freeze unnecessary expenses, pause non-performing ads |
| Day 2 | Relaunch monetizing funnels (courses, certifications) |
| Day 3 | Tool usage audit + WhatsApp journey review |
| Day 4 | MIS dashboard setup + salary alignment review |
| Day 5-6 | Team realignment + course push offers + flash sales |
| Day 7 | Review progress, close 5 paid upsells, founders review |

# 13. June 2025 Monthly Objectives by Vertical

Overall Revenue Target: Rs 65 Lakhs

| Vertical | Target (Rs L) | Key Goals / Tasks |
| --- | --- | --- |
| Beep Learn | 55 | Internship Courses live; Team size increase; Biweekly consultant reviews; Weekly review with Diwakar; Launch new programs |
| Certificates | 3 | Drive certification bundling with career planner; Weekly nudges for job seekers; Bundle with Pro Plan |
| Pro Plan | 3 | Free Trial experiments (Rs 1 trial -> Rs 99); Personalized onboarding; On-app nudges; Sticky CTA |
| BeepHire | 5 | Closures push; Recruiter WOW experience; Talent pool system; WhatsApp bot refinement; Sales sprint |
| UniBeep | 5 | Key accounts setup; Consultant systems; Daily tracking discipline; Integration partners |

## 13.1 Networking & Fundraising Goals

- Pune, Mumbai, Bangalore investor + founder meetings

- Mentor/Investor check-ins and office meet-up hosting

- Close Rs 3-15 Cr round with follow-up pipeline, demo updates, MIS

# 14. Product Ownership & June Deliverables

| Vertical | Product Ownership Areas | Deliverables | Metric/Target | Deadline |
| --- | --- | --- | --- | --- |
| Beep Learn (Rs 55L) | Course automation, Resume-to-recommendation upsell, Quality dashboard | Beep Learn journey automation, Integration with resume & AI planner, Course QA tracker | 3 live automated funnels, 100% course QA logged, <3 day dev turnaround | 15 June |
| Certificates (Rs 3L) | Career Planner integration, Payment-to-PDF flow, Bundle offers | Certificate CTA post roadmap, 1-click cert PDF via WA+app, Rs 98+Rs 99 bundle | CTR > 5%, <60s cert delivery, Rs 1.5L via bundle | 10 June |
| Pro Plan (Rs 3L) | Free trial system, WOW onboarding, Homepage nudges | Rs 1 trial -> auto renewal, Personalised WOW onboarding, Sticky CTA | Trial->Paid >= 20%, 100% onboarding, <5 clicks to upgrade | 18 June |
| BeepHire (Rs 5L) | Recruiter dashboard, Sourcing engine, WA bot flows | JD->Candidate match UX v2, Talent pool visibility, WA bot status updates | <24h TAT for reports, Source pool 500+/week | 25 June |
| UniBeep (Rs 5L) | TPO dashboard QA, Analytics, Partner onboarding | Reports for TPOs, Bulk upload, Activity email triggers | 10 colleges actively using, 100% usage logging | 20 June |
| Beep App (Rs 3L) | Home personalization, Campus referral, Career journey sync | Leaderboard+streak UI, Campus invite flow, Career map->course match | DAU/MAU +20%, Referral installs >10K, 60% see roadmap | 28 June |

# 15. UI/UX Career Program — Full 16-Week Curriculum

Duration: 4 Months (16 Weeks) | Format: Live + LMS (Edmingle) + Assignments + Projects | Tracks: Visual UI Design, UX Research, UX Writing, Design Systems, Prototyping, AI Tools, Analytics, Product Thinking, Portfolio, Job Preparation. Resources: 1 Program Coordinator, 2 in-house mentors, 7-8 external mentors, 2 hiring supports (shared), 1 LMS (Edmingle), Google Sheets for batch management. Currently 17+ batches running with weekday and weekend variants.

| Phase | Weeks | Module | Core Focus | Outcome |
| --- | --- | --- | --- | --- |
| FOUNDATION | 1-2 | Design Thinking & UX Fundamentals | UX Mindset, Problem Framing, Heuristics, Research | User-first thinking, brief writing |
| TOOLS & UI | 3-4 | UI Systems + Tool Mastery (Figma) | Grids, Typography, Color, Layouts, Components | Tool mastery, submission-ready screens |
| PROCESS & FLOWS | 5-6 | UX Process + Information Architecture | Journey Mapping, Wireframing, Sitemaps, Whiteboarding | UX flows, IA for real problems |
| VISUAL DESIGN | 7-8 | Branding + Visual Storytelling | UI Patterns, Design Systems, Micro-interactions | Style guides, visual themes |
| AI & FUTURE | 9 | AI Tools in UI (Uizard, Leonardo, GPT) | AI Prompting, UI by Prompt, Rapid Prototyping | AI-assisted UI building |
| ANALYTICS | 10 | UX Analytics & Testing | Google Analytics, Hotjar, A/B Testing, UX Metrics | Data-driven design decisions |
| CASE PROJECTS | 11-12 | Case Study: Real Brand Redesign | End-to-End UX/UI project, Presentation | Industry-grade portfolio piece |
| PORTFOLIO & JOBS | 13-14 | Resume, Portfolio, Interview Prep | Website, Resume, LinkedIn, Mock Interviews | Job-ready, BeepHire-profile ready |
| INTERNSHIP | 15-16 | Internship/Client Project | Real assignments via Hire.ai or client briefs | Live project, career tracker entry |

## 15.1 Module Details

- Module 1 (Wk 1-2): UX Foundations — What is UX, UX Laws & Heuristics, Design Thinking Process, Persona Creation, Empathy Maps, Problem Statements. Deliverables: UX Audit, User Persona, Empathy Map, Problem Brief.

- Module 2 (Wk 3-4): Figma & UI Systems — Figma Deep Dive (Frames, Auto Layout, Constraints, Components), Visual Design (Color, Typography, Spacing), Grid Systems, UI Kits & Design Tokens, Style Guides. Deliverables: Component Library, Style Guide, Homepage UI.

- Module 3 (Wk 5-6): UX Process & Wireframing — User Flows & Task Flows, Information Architecture, Wireframes Lo-Fi to Mid-Fi, Whiteboarding Challenges, UX Writing/Microcopy, Accessibility. Deliverables: Sitemap, Wireframes, Whiteboarding Solution, Accessibility Audit.

- Module 4 (Wk 7-8): Visual Design & Case Project 1 — Visual Hierarchy, Color Psychology, Branding, UI Animation Basics, Capstone Brief (real-life redesign). Deliverables: Design System, Case Study #1, Presentation Deck.

- Module 5 (Wk 9): AI Tools — Prompt-Based UI Design (Uizard, Leonardo, GPT-4), Design from Prompt, GPT for UX Writing, Role of AI in UX. Deliverables: Prompt-to-UI Assignment, GPT Copywriting Task, Reflection Report.

- Module 6 (Wk 10): UX Analytics — Google Analytics, Hotjar/Crazy Egg/Maze, A/B Testing 101, UX Metrics (SUS, task success), Usability Testing. Deliverables: Heuristics Evaluation, A/B Testing Plan, Analytics Report.

- Module 7 (Wk 11-12): Portfolio & Interview — Personal Branding, Behance/Dribbble, Resume Writing (ATS-friendly), BeepHire/LinkedIn profiles, Mock Interviews. Deliverables: Final Resume, Portfolio Website, Mock Scorecard.

- Module 8 (Wk 13-16): Internship — Internship Assignment via Hire.ai, Design Handoff for developers, Feedback Integration, Final Certification and Graduation.

# 16. Session Types & Learning Formats

| Session Type | Frequency | Details |
| --- | --- | --- |
| Live Mentorship | 2-4/week | Concept + walkthrough + discussion-based learning |
| Whiteboarding Rounds | Weekly | Scenario-based UX thinking (Zoom Whiteboard, Miro, Figma Jam) |
| Figma Hours | Biweekly | Instructor screenshare + student mimic in real-time, tool deep-dives |
| Mock Interviews | Once/month (from Wk 6) | 1:1 Mock (Mentor or Alumni), scored by rubrics + video feedback |
| AI Prompt Labs | Every 3 weeks | Leonardo, Uizard, GPT for UI generation, AI-driven persona simulation |
| Masterclasses | Fortnightly | External speakers: design leaders, product designers, AI UX pros |
| Analytics & Testing | Weeks 6, 10, 14 | Usability audits, A/B Testing, Google Analytics + Hotjar demos |
| Project Showcase Day | End of Month | Each student presents live, judged by 2 mentors/alumni |
| Alumni SME Sessions | Ad-hoc | 1 SME handles peer doubts for every 15-20 students |
| Peer Review Circles | Weekly (from Wk 3) | Structured feedback exchanges between students with scoring grids |

# 17. Milestones & Submissions (Revised — Accelerated)

Mock interviews and portfolio building start as early as Week 5-6 to fast-track hiring readiness.

| Week | Day | Milestone | Type | Format | Reviewed By |
| --- | --- | --- | --- | --- | --- |
| 1 | 1-7 | Orientation + Problem Statement + Persona + Empathy Map | Foundation | Google Doc | Mentor |
| 2 | 8-14 | Journey Map + UX Research Report | Major Milestone | PDF/Slides | Mentor + Coordinator |
| 3 | 15-21 | Signup + Home Wireframes (Low/Mid-Fi) | Design Output | Figma | Mentor |
| 4 | 22-28 | First Visual Mockups + UI Polish (2-3 screens) | Visual Design | Figma | Mentor |
| 5 | 29-35 | Portfolio v0 (First Draft) Submission | Major Milestone | Notion/Figma/PPT | Mentor + QA |
| 6 | 36-42 | Mock Interview Round 1 + Resume Draft | Evaluation | Scorecard+Doc | Mentor |
| 7 | 43-49 | Final Portfolio Direction Locked | Review Task | QA Sheet | Mentor |
| 8 | 50-56 | Case Study 1 Final + Resume Finalization | Submission | Figma+PDF | Mentor + Hiring |
| 9 | 57-63 | Portfolio v1 (Minimum Viable) Ready + Peer Review | Readiness Check | Final Link | Coordinator + Peer |
| 10 | 64-70 | Internship Design Task Phase 1 | Job Prep | Screenshots+Figma | Hiring Support |
| 11 | 71-77 | Mock Interview Round 2 (Advanced) | Job Simulation | Updated Scorecard | Mentor + Coordinator |
| 12 | 78-84 | Final Portfolio Polish + Internship Task Phase 2 | Visual QA | Screens+Notes | Mentor + Hiring |
| 13 | 85-91 | BeepHire Profile + LinkedIn Optimization | Profile Task | Profile Links | Coordinator |
| 14 | 92-98 | Final Job QA + Personal Branding Assets | Readiness Check | Sheet+Visual Assets | Hiring Support |
| 15 | 99-105 | Final Mentor Review + Fixes | Cert Review | Sheet+Comments | Mentor + Coordinator |
| 16 | 106-112 | Graduation + Certificate + Referrals | Certification | Auto-generated | Coordinator + Biz Head |

# 18. Program Automation & Quality Systems

## 18.1 Automation Stack

| Automation | Tool | Trigger | Output |
| --- | --- | --- | --- |
| LMS Progress Sync | Edmingle | Weekly: attendance + assignment % | Progress graph in dashboard |
| Assignment Submission Alerts | Google Sheets + Gmail API/Zapier | Deadline missed by 48h | Email + WA warning to student |
| Session Recording Upload | Google Calendar + Notion | After mentor ends call | Slack ping + LMS update |
| Late Submission Flagging | Google Apps Script | LMS to tracker sync | Red flag row in dashboard |
| Auto Nudge Emails | Zapier + Gmail | No login > 7 days | Email + mentor CC |
| Batch Health Scoring | Google Data Studio | Aggregates from LMS + Sheets | Red/Yellow/Green tagged batches |
| Portfolio QA Queue | Google Form | Form submit -> Sheet tracker | Added to mentor QA queue |
| Certificate Ready Flag | Sheet Formula | All fields marked | Coordinator notified to issue cert |

## 18.2 Quality Control

- Weekly: Mentor Delivery Tracker (session logs + attendance), Student Participation Dashboard, Standardized Review Rubrics

- Monthly: Mentor Performance Review (punctuality, NPS, QA from peer mentor), Student NPS Form (anonymous, 10-point), Session Quality Score (auto-flag poor sessions)

- Session-Level: Post-session Google Form auto-triggered, 4-point rubric (Understanding, Execution, Effort, Creativity), Internal QA Reviews of top/bottom 10% assignments, Mentor Swap System for inactive mentors

# 19. Student Progress Tracking & Batch Management

## 19.1 Batch Structure

| Unit | Owner | Responsibility |
| --- | --- | --- |
| Batch | Program Coordinator | Overall batch operations, alerts, tracking setup |
| Mentor (1:25) | In-house or Assigned SME | Delivery, session logs, reviews, mock interviews |
| Support Buddy | Alumni (1:15 students) | Peer queries, submissions check, FAQs |
| Hiring Liaison | Shared team | Profile readiness, portfolio collection |

## 19.2 Graduation Eligibility (Auto-Tracked)

- Final Portfolio Submitted and QA Reviewed

- Resume Approved (QA score > 7)

- Mock Interview Completed (score > 6.5)

- Attendance > 80%

- All Major Projects Submitted

- If any flag fails -> student enters 'Improvement Lane' with extra 2 weeks support

# 20. Program Outcomes & Skill Benchmarks

## 20.1 Skill-Based Outcomes

| Category | Outcome |
| --- | --- |
| UX Research | Conduct interviews, surveys, persona creation, empathy/journey mapping independently |
| Information Architecture | Create clear site maps, user flows, task flows |
| Wireframing | Design mid-fidelity wireframes using Figma for multi-screen flows |
| Visual Design (UI) | Apply typography, spacing, colors, iconography, UI patterns consistently |
| Prototyping | Build clickable Figma prototypes with transitions and hover states |
| Design Systems | Create scalable style guides, UI kits, reusable components |
| UX Writing | Write usable microcopy, CTAs, error messages |
| Accessibility | Apply WCAG principles to UI |
| AI in Design | Use AI tools for ideation, content generation, design prompting |
| Analytics | Understand behavior metrics (bounce, retention, funnel) to iterate UI |

## 20.2 Placement-Readiness Benchmarks

| Metric | Minimum Target |
| --- | --- |
| Portfolio Rating | 7/10 (Mentor QA reviewed) |
| Mock Interview Score | >6.5/10 in final round |
| Resume Review | No flags from hiring support |
| Internship Task | Completed Beep Live Internship project |
| Interview-Ready | By Week 10 (early mover access) |
| Certification Criteria | Attendance >80%, Submissions >90%, Final QA cleared |

# 24. CEO Operating System & Vertical North Stars

## Operating Principles

- One number per vertical (North Star) + three input metrics. Everyone knows the weekly target.

- Owners, not meetings. Every metric has Owner, Target, Deadline, Playbook, Escalation.

- Asynchronous first. Standups written + dashboards auto-post in Slack.

- Ship weekly; prove monthly. Every team ships a weekly 'value artifact'.

- Meritocracy + sunlight. Public leaderboards, SPIFFs, PIPs for underperformance.

- Guardrails > micromanagement. Pre-agreed ranges for CAC, payback, refund %, NPS.

## Vertical North Stars & Guardrails

| Vertical | North Star | Inputs | Guardrails |
| --- | --- | --- | --- |
| Beep App | Pro Plan MRR (Rs) | Installs->Signups->D0 activation->Trials->Trial->Paid % | CPI<=Rs 7, Trial->Paid>=7-10%, W1/W4>=25%/10%, Payback<=6wk |
| Beep Learn | Cash Collected/Month | QLs->Showups->Enrolments->Completion %->Interviews | Refund<=6%, GM>=70%, Mentor:Student<=1:40, NPS>=55 |
| BeepHire | MRR (SaaS + fees) | SDR demos/day->AE win %->Jobs posted->Jobs filled <=3h | Demo->Win>=25%, Churn<=3%/mo, TTFS<=24h |
| UniBeep | New Colleges / ARR | TPO demos->MoUs->Activation (30d) | Cycle<=45d, Activation>=70%, SLA<24h |

## CEO Daily Dashboard (Auto-posted 9:15 AM)

- Top Strip: Today/MTD Revenue, CM%, Cash banked, Runway (months), Blended CAC, DAU

- Beep App Panel: Installs->Signups->D0->Trials->Paid; W1/W4 cohorts; ARPU; CPI/CAC

- Beep Learn Panel: QLs, Showups, Enrolments, Cash-in, Refund rate, Completion %, NPS

- BeepHire Panel: Demos set/done, New logos, Jobs posted/filled, MRR net, CS tickets

- UniBeep Panel: Demos, MoUs, Colleges live, Students onboarded, Activation %, ARR

- Pacing View: Red/amber/green bars with gap to target and suggested fix plays

- Alert banners: guardrail breaches for 48h, refund spikes, CAC spike, trial->paid drop

## CEO Time Allocation

| Focus | % Time | Activities |
| --- | --- | --- |
| Revenue & Distribution | 40% | Daily war-room, top 20 partners, creator network, pricing |
| People & Hiring | 30% | A-players, coach GMs, remove blockers, PIPs/exits fast |
| Product Direction | 20% | Top 3 bets, kill bottom; customer calls |
| Capital & Narrative | 10% | Investor updates, PR, strategic alliances (ME/US/UK) |

# 27. December 2025 — Full 360-Degree Review

North-star (Dec): Company revenue target ~Rs 55L with strict cost cut Rs 5-10L/mo and active fundraise (Rs 2-10 Cr).

Core Issue: Performance discipline & motivation uneven; blockers reported but not owned; product usage data to decisions loop slow; cross-vertical handoffs weak.

## December OKRs

| Vertical / Area | Target / OKR |
| --- | --- |
| Company Revenue | Rs 40-45L total |
| Net Loss Containment | <= Rs 8-12L while cutting Rs 10-15L costs |
| Bridge Round | Rs 1.2 Cr signed; Rs 2-5 Cr additional in pipe |
| Beep App Pro MRR | Rs 7-15L; DAU >= 10K; W1 >= 25-35%, W4 >= 12% |
| Beep Learn Revenue | Rs 25-35L (>= 60% GM); ROAS >= 2.0x; NPS 45-50; 3+ micro programs live |
| BeepHire Revenue | Rs 5L; Demo->Paid >= 20% on focused roles; 50-60 leads/day automated |
| UniBeep | New paid colleges >= 4-6; Collections: clear overdue + Rs 3-5L fresh |
| Cost Cutting | Rs 10-15L/month objective |
| Fundraise | Rs 1.2Cr near-term; Rs 7-8Cr conversation started |

## Key Issues from December Meetings

- Revenue vs Runway pressure: December target Rs 55L but verticals behind pipeline; Jul'25 actual was Rs 37.1L

- Cost structure too heavy: Direct costs Rs 24-26L/mo, Indirect Rs 26-28L/mo vs revenue

- Motivation & accountability: Teams not called out for low performance; daily huddles = updates not outcomes

- Fragmentation across 4 verticals: CEO time split; no single exec dashboard

- Data confidence gaps: Mixpanel events not sorted; retention funnels missing; no daily truth dashboard

- Beep App: Retention/engagement below plan; Pro conversion soft; feature sprawl; acquisition skewed to paid

- Beep Learn: Delivery quality/NPS fluctuates; lead gen too ad-led; micro-ticket programs not launched

- BeepHire: Low demo->close rate; AI call quality/scoring errors; lead gen automation WIP; Head not hired

- UniBeep: Demo->closure ratio low; onboarding automation incomplete; consultant network partly set

- Cross-functional: Lifecycle messaging not standardized; Mixpanel discipline missing; WOW moments not defined

# 29. Financial Statement Review (FY24-25)

## Key Highlights

- Revenue (Operations): Rs 1.96 Cr (FY25) vs Rs 87.8L (FY24) — ~2.2x growth

- Total Expenses: significantly higher — Professional Fees Rs 65.46L, Marketing Rs 70.39L, Employee Benefits Rs 36.40L

- Net Loss: ~Rs 2.53 Cr (FY25)

- Current Ratio: 0.28 — severe cash stress (current liabilities Rs 90.3L)

- Net Worth: Negative — board needs explicit plan + narrative

- Loans from Saurabh: Rs 11.32L (FY25), Interest paid: Rs 1.32L

- Remuneration: Saurabh Rs 12.25L, Rakhi Rs 10.50L

- GST late fees and TDS interest exist — filing slippages flagged

- Trade receivables Rs 2.63L but current liabilities Rs 90L — working capital mismatch

- Short-term provisions Rs 28.37L and other current liabilities Rs 15.26L need detailed schedules

- Donation Rs 8.08L — needs compliance check + board approval verification

## Filing-Readiness Checklist

- Bank reconciliation statements (all accounts) + OD confirmation

- Vendor confirmations for top payables (especially professional fees)

- Statutory dues summary: GST/TDS/PF/ESI (paid + pending + late fees reasons)

- Related party register + board resolutions pack

- Share capital / shareholding reconciliation with ROC forms and cap table

- Going concern narrative (loss + negative net worth + low current ratio)

# 33. 2026 Goals, OKRs & Strategic Direction

Theme: Prove repeatable growth + margins in 1-2 core engines, cut distractions, build A-team operating system.

## Engine Prioritization

| Priority | Vertical | Rationale | 2026 Goal |
| --- | --- | --- | --- |
| Engine A (Cash) | Beep Learn | Already generates meaningful revenue | Most trusted Job-Ready Program engine with repeatable sales + high outcomes |
| Engine B (Scale) | Beep App (Pro) | Long-term distribution + subscription | Next-gen LinkedIn for college students: daily habit + paid upgrade |
| Gate 1 | BeepHire | Keep only if repeatable | Narrow ICP + best-in-class for 1-2 roles with WOW shortlist |
| Gate 2 | UniBeep | Keep only if cash collection works | Predictable college sales + cash collection + renewals |

## 2026 Quarterly Plan

| Quarter | Focus | Key Actions |
| --- | --- | --- |
| Q1 | Focus + Cleanup | Kill low-impact work; Lock dashboards + weekly cadence; Pick 2 engines, set gates for 2 others |
| Q2 | PMF Proof | Push retention improvements in App; Make Learn repeatable with strong outcomes |
| Q3 | Scale What Works | Increase spend only where payback proven; Expand programs/partnerships carefully |
| Q4 | Expansion (if ready) | US/Middle East/UK only if: Learn has repeatable outcomes + App has improved retention |

# 36. Impact Metrics & Placement Targets (FY26)

Company North Star: 10,000 students get job-ready, 5,000 students get placed (job/internship)

Baseline: BeepHire placed 550 students last year (confirmed).

| Vertical | Purpose | FY26 Target | Key Metric |
| --- | --- | --- | --- |
| BeepHire | Convert hiring demand into offers | 2,000 placements (~4x) | Offer conversion rate; Hiring success rate |
| Beep Learn | Make students job-ready -> hiring funnels | 1,800 placements (3000 eligible x 60%) | Placement within 120 days of completion |
| UniBeep | Campus outcomes at scale | 1,500 placements (25 colleges x 200 x 30%) | 30% placement rate of active final-year students |
| Beep App | Massive top funnel impact | 500-1,000 tracked + 100K career-active | Career activation (3+ monthly actions) |

Rule: No impact metric is counted unless measurable. Each vertical must track: Unique student ID, Program/college/source tag, Placement proof status (offer/joining/interview).

# 40. Key Metrics Reference & Recognition

| Metric | Value |
| --- | --- |
| Monthly Revenue (May 2025) | Rs 25L+ |
| Monthly Active Users | 70K |
| DAU | 8.9K |
| App Installs | 3L+ (300,000+) |
| Student Database | 4M+ profiles |
| CAC | Rs 20/student |
| Burn Rate | Rs 9L/month (target) |
| College Tie-ups | 800+ colleges |
| Recruiter Partners | 8,000+ (per deck: 8,550) |
| EdTech Partners | 120+ |
| Opportunities Listed | 10,800+ |
| Revenue FY24-25 (audited) | Rs 1.96 Cr (ops) / Rs 3.1 Cr (per deck) |
| 3x YoY Growth | Confirmed |
| 75% Organic Acquisition | Confirmed |
| Avg Time Spent | ~32 mins daily |
| Current Ratio (FY25) | 0.28 |
| Key Investors | SucSeed Indovation, Ashneer Grover, Aman Gupta, Peyush Bansal |
| Shark Tank Raised | Rs 30L |
| CCD Raised | ~Rs 10 Cr |
| Valuation Reference | ~Rs 50 Cr (~$6M) |

## Recognition & Awards

- Shark Tank India — Featured and funded

- SucSeed Indovation Fund — Institutional investor

- Google Appscale Academy — Accelerator

- NUMA — Accelerator

- CM Maharashtra Award

- Global Student Entrepreneur Award (GSEA)

- Media: Hindustan Times, YourStory, major outlets

# 21. Program Setup Checklist (Team Execution)

This checklist ensures all systems, content, operations, automations, and student success workflows are covered. Designed for: Mentor 1, Mentor 2, Program Coordinator, Business Head.

## Section A: Curriculum & Content Setup

| Item | Owner | Format | Status |
| --- | --- | --- | --- |
| Final 16-Week Curriculum | Mentor 1 + Biz Head | Google Doc / Notion | Required |
| AI + Analytics Modules Embedded | Mentor 2 | Slides + Masterclass Doc | Required |
| UX Case Study Framework | Mentor 1 | Notion / PDF | Required |
| Portfolio Checklist (V1 & Final) | Mentor 2 | Google Sheet | Required |
| Figma Assignments (30+ prompts) | Mentor 1 | Figma + Sheet | Required |
| Master Deck Library | Coordinator | Google Drive | Required |
| Research + Visual Style Templates | Mentors | Notion + Figma Templates | Required |
| Update system for curriculum improvements | Biz Head | Process Doc | Required |

## Section B: Batch Structure & Operations

| Item | Owner | Format | Due |
| --- | --- | --- | --- |
| Batch Calendar (all sessions) | Coordinator | Google Calendar | Before Start |
| Batch Folders on Drive | Coordinator | Google Drive | Before Start |
| Student Submission Form | Coordinator | Google Form + Sheet | Before Start |
| Session Log Template | Mentors + Coordinator | Google Sheet | Before Start |
| Attendance Tracking Sheet | Coordinator | Zoom CSV + Sheet | Before Start |
| Batch Status Tracker | Coordinator | Google Sheet | Before Start |
| WhatsApp Groups + Templates | Coordinator | Google Doc | Before Start |
| Escalation SOP | Coordinator | Doc | Before Start |

## Section C: Student Onboarding

| Item | Owner | When |
| --- | --- | --- |
| Onboarding Form (goals, tools, language) | Coordinator | Before Start |
| Welcome Deck (rules, culture, tools, outcomes) | Coordinator | Day 1 |
| Student Roster in sheets + Notion | Coordinator | Day 1 |
| Support Buddy assigned per batch | Coordinator | Week 1 |
| Peer Review System initiated | Coordinator | Week 3 |
| Central Resource Folder shared | Coordinator | Day 1 |
| Figma/Notion/Google access ensured | Coordinator | Day 1 |
| Personal Career Tracker shared | Coordinator | Week 2 |

## Section D: QA & Review System

| Item | Owner | Format |
| --- | --- | --- |
| Submission Tracker per batch (auto-flag late) | Coordinator | Google Sheet |
| Rubric for each milestone documented | Mentors | Google Form + Sheet |
| Portfolio QA Rubric linked to evaluation | Mentor 1 | Google Form |
| Resume QA Rubric shared with students | Hiring Support | Google Sheet |
| Mock Interview Calendar (from Week 6) | Mentor 2 | Calendly / Sheet |
| Hiring Scorecard Sheet (0-10 scale) | Hiring Support | Google Sheet |
| Feedback Forms configured | Coordinator | Google Forms |
| Warning triggers documented | Coordinator | Google Sheet |

## Section E: Automation & Reporting

| Item | Tool | Trigger | Output |
| --- | --- | --- | --- |
| Late submission alerts | Apps Script | 48h after due | Email to student + CC mentor |
| Attendance below 80% flag | Weekly Scan | Sheet formula | Red highlight + email alert |
| Portfolio status to hiring team | Zapier | On approval | Notify hiring support |
| Weekly Digest Report | Apps Script/Manual | Every Friday | Batch health to all stakeholders |
| Cert-ready filter formula | Sheet Formula | All flags green | Coordinator notified |
| Career Output Dashboard | Data Studio | Auto | Cert %, job %, avg rating for Biz Head |
| Referral System | Sheet + Process | Top performers | Activate for ambassador pipeline |
| Auto-cert generation | Edmingle/Sheet | Final approval | Certificate issued |

## Section F: Business Metrics & Outcomes

| Item | Owner | Cadence |
| --- | --- | --- |
| Placement Tracker Sheet | Hiring Support | Weekly update |
| Certification Rate monitoring | Coordinator | Weekly |
| Batch-wise Completion Report (Revenue vs Outcome) | Biz Head | Monthly |
| Mentor NPS aggregation | Biz Head | Monthly |
| Profitability model per batch (Fee x Students - Cost) | Biz Head | Per batch |
| Exit Interviews with students | Coordinator | Final week |
| Referral NPS Scorecards | Coordinator | Monthly |

# 22. Team Touchpoints & Cadence Table

| Week/Frequency | Team Role | Touchpoint / Action | Purpose | Format |
| --- | --- | --- | --- | --- |
| Day 0 | Coordinator | Kickoff onboarding + Tool setup | Set expectations, tool access | Zoom + Welcome Deck |
| Day 1-2 | Mentor | 1:1 Icebreakers + Goal Form | Understand needs, experience | Form + Mini Zoom |
| Weekly (Mon) | Coordinator | Attendance + submission audit | Review who's lagging | Sheet + Automation |
| Weekly (Mon) | Biz Head | Batch Health Overview | Track completion %, NPS | Dashboard |
| Weekly (Tue) | Mentor | Live session delivery | Syllabus + hands-on demo | Zoom + Slides/Figma |
| Weekly (Wed) | Coordinator | Peer Review Round | Peer feedback on projects | Google Form + Pairs |
| Weekly (Thu) | Mentor | QA Review + Doubt Resolution | Clear backlogs, review quality | Zoom + Sheet |
| Weekly (Fri) | Coordinator | Auto-flag warnings + Weekly nudge | Nudge lagging students | WA + Email |
| Biweekly | Mentor | 1:1 student check-in (at-risk) | Intervention for struggling students | Zoom / WA |
| Biweekly | Students | NPS Feedback Form | Session + mentor quality tracking | Google Form |
| Monthly | Biz Head | Mentor Performance Review | Quality, NPS, session coverage | Sheet + Review |
| Week 5 | Mentor | Portfolio v0 Review | Early portfolio direction | Figma + Notion |
| Week 6 | Mentor | Mock Interview Round 1 | Build confidence, identify gaps | Zoom + Scorecard |
| Week 9 | Coordinator + Peer | Portfolio v1 Peer Review | External review + refinement | Form + Review |
| Week 10 | Hiring Support | Resume + BeepHire profile review | Job pipeline readiness | Sheet + Profile Links |
| Week 12 | Mentor | Mock Interview Round 2 (Final) | Simulate real hiring | Panel + Scorecard |
| Week 14 | Hiring Support | Job QA + Branding Assets | Final readiness check | Sheet + Assets |
| Week 16 | All | Graduation + Certificate | Official completion | Auto-cert + Event |

# 25. Meeting Cadence & Execution Rituals (Full)

## 25.1 Daily Cadence

8:45-9:00 AM: Asynchronous standups in Slack/Notion per squad. Format: Yesterday wins, Today commitments, 1 blocker. No storytelling.

9:30-10:00 AM: Revenue War-Room (CEO + GMs + RevOps). Review MTD pacing vs plan (<=30 min hard stop). Pick 3 moves for next 24h. Assign owners; log in War-Room Kanban.

## 25.2 Weekly Cadence

| Day | Meeting | Duration | Led By | Purpose |
| --- | --- | --- | --- | --- |
| Mon PM | Product Council | 90m | CEO + CTO + PMs | Roadmap vs outcomes. Decide top 3 bets, what to kill. |
| Tuesday | Vertical WBRs | 60m each | Each GM runs WBR packet | Last week vs target, what worked/failed, funnel drops, experiments, 3 commitments |
| Wednesday | Interlock | 60m | All dept heads | Cross-team dependencies; re-prioritize shared resources |
| Thursday | People & Finance | 60m | COO + CEO | Hiring pipeline, PIPs/recognitions, cash pacing, vendor spends |
| Friday | Demo Day | 45m | All pods | Every pod shows a live ship (feature, creative, script, deck, automation). Celebrate wins. |

## 25.3 Monthly / Quarterly

MBR (2h): P&L by vertical, cohort health, unit economics, retention, NPS. Greenlight/kill lines.

QBR (half-day): Strategy reset, 3 company bets, budget shifts, org changes.

Meeting Hygiene: Pre-reads only; no screen-scraping metrics; end each with 3 decisions + owners + dates.

## 25.4 WBR Packet (Auto-generated)

- Header: Target vs Actual (Week + MTD), variance %, why

- Funnel: counts + rates at each step; top 3 drop-offs

- Experiments table: hypothesis, owner, dates, result, decision (scale/kill)

- P&L mini: revenue, CM%, CAC, payback, refunds

- Upcoming 7 days: 3 moves, owners, expected impact

- Risks & asks to interlock/CEO

# 26. Incentives, Motivation & Performance System

## 26.1 Compensation Model

| Role Type | Compensation Structure |
| --- | --- |
| GMs | Fixed + 10-15% variable on P&L target (revenue & CM% weighted 70/30) + SPIFFs for beating plan by 10%+ |
| Sales (BeepHire/UniBeep/Learn) | OTE with accelerators (1.3x commission beyond 110% quota) |
| Growth | Variable on paid conversions/ARPU and CAC/payback within guardrails |
| PMs/Engineers/Design | Quarterly bonus on adoption, retention lift, revenue-linked outcomes |

## 26.2 SPIFFs (30-day Bursts)

| Vertical | SPIFF Criteria |
| --- | --- |
| Beep App | +Rs X per 1000 trials at <= Rs Y CAC; +Rs X for hitting W1>=27% |
| Beep Learn | +Rs X per 50 enrollments with refund <=4% |
| BeepHire | +Rs X per 20 jobs filled <=3h; logo wins SPIFF |
| UniBeep | +Rs X per 5 MoUs closed within 30 days & activation >=70% |

## 26.3 Recognition & Energy

- Friday 'Golden Beeper' (peer-nominated): Rs 10K voucher + LinkedIn shoutout

- Learning wallet (Rs 3-5K/person/quarter) tied to sharing a 20-min teach-back

- Transparent scoreboards on TV/Slack — celebrate green weeks; dissect reds without blame

- Monthly 'Founder AMA' with raw numbers for full transparency

- Customer days: each leader spends 2 hours/week with students/recruiters/TPOs

## 26.4 Low Performance Protocol

| Timeline | Action |
| --- | --- |
| Week 1 | Coaching + crystal targets (written). Clear KPIs documented. |
| Week 3 | If no movement, PIP 30 days (weekly measurable goals). |
| Week 7 | Role change or exit. Maintain bar. High talent density is a moat. |

# 30. Founder's Office — Role & Structure

One-line: Founder's Office = CEO's execution engine — turns Saurabh's priorities into weekly outcomes, keeps every vertical accountable, runs on numbers + decisions.

## 30.1 Core Responsibilities

| Responsibility | What They Actually Do |
| --- | --- |
| CEO Priority Management | Convert goals into quarterly OKRs -> weekly goals -> daily must-wins. Protect CEO time. |
| Business Rhythm + Accountability | Own daily huddle structure (numbers + output + blockers). Own weekly reviews per vertical. Enforce decisions + owners + due dates. |
| KPI Dashboard + Insights | Build and maintain CEO cockpit. Daily: revenue vs target, pipeline, spend, retention. Weekly: what moved, what broke, what next. |
| Cross-functional Execution | Special projects: Pro plan sprint, Learn launch playbook, UniBeep sales motion, BeepHire redesign, cost cutting, fundraising data room. |
| Internal Comms + Culture | Set performance culture: weekly wins + misses, clear expectations, escalation, make leaders report like owners. |

## 30.2 Skills Required

- Numbers thinking: Comfortable with funnels, CAC, ROAS, revenue, collections, churn — can spot anomalies

- Operating discipline: Can build systems (dashboards, SOPs, templates, meeting rhythms) for 60-80 person team

- High-agency execution: Doesn't wait for instructions; sees problem, fixes, follows up, closes

- Stakeholder management: Can push leaders without being rude; escalate to CEO with clarity and options

- Written clarity: Can write crisp one-pagers with issue, root cause, options, recommendation

## 30.3 Ideal Structure

| Role | Focus | Reporting |
| --- | --- | --- |
| Founder's Office Lead (Chief of Staff) | CEO dashboard + meeting cadence + execution tracker + special projects | Reports to CEO |
| RevOps / Data Analyst | Dashboards + reports + attribution + pacing models | Reports to FO Lead |
| Program Ops (optional) | Beep Learn delivery + NPS + refunds + placement ops tracking | Reports to FO Lead |

## 30.4 FO Scorecard (30/60/90 Days)

| Timeline | Success Criteria |
| --- | --- |
| 30 days | Dashboards + meeting system locked; CEO sees 1 dashboard daily |
| 60 days | Metrics stable; leaders reporting cleanly; low performance flagged |
| 90 days | Revenue & execution velocity improves because focus improves |

# 31. Founder Alignment Meeting Structure

One-off 3-founder alignment meeting (3-4 hours) to lock vision + priorities + org structure + next 30/90 days.

## Pre-Read (Each Founder Submits)

- Top 5 problems killing speed/PMF

- Top 5 priorities for next 90 days

- 3 decisions wanted from founders today

- Non-negotiables (what you refuse to compromise on)

- Current scorecard (revenue, burn, runway, App/Learn/Hire/UniBeep funnels)

- Org list (all leads + what they do today)

## Agenda

| Block | Time | Purpose | Output |
| --- | --- | --- | --- |
| Opening Alignment | 15 min | 'What problem are we solving?' + '12-month goal' | Shared mission + 12-month outcome target |
| Reality Check | 30 min | Current revenue, burn, runway, PMF signals, team gaps | Agreed truth snapshot |
| Strategic Focus Decision | 45 min | Pick 2 engines + 2 gates; decide operating model | Which engines to scale vs gate |
| Vertical Targets | 60-75 min | PMF metric, 90-day goal, top 3 levers, top 3 risks, what to STOP | 1 page per vertical |
| Org Structure | 45-60 min | Team architecture, founder ownership, talent plan (top/bottom 20%) | Org chart + RACI + 30-day people plan |
| Execution System | 30-40 min | Dashboards, weekly cadence, escalation rules, performance rules | CEO dashboard + WBR format + PIP rules |
| Decision Log | 20 min | Top 10 decisions with Owner, Deadline, Metric | Decision tracker |
| 30-Day Sprint | 15 min | Top 5 priorities, assign owners, set checkpoints | Sprint plan |

## Deliverables to Walk Out With

- Beep 90-day strategy (1 page)

- Vertical targets (4 pages max)

- Org chart + founder ownership map

- Hiring / restructuring plan (30 days)

- Decision tracker + sprint plan

- Meeting cadence + dashboard templates

# 34. Growth & Acquisition Plan to 10M Users

| Stage | Tactics | Goal |
| --- | --- | --- |
| Awareness | Meta ads, Google UAC, WhatsApp viral flows, student influencer flywheels | 2M installs by Sep '25 |
| Activation | Resume upload -> AI roadmap -> community unlock -> Pro Plan trial | 70% activation rate |
| Retention | Career tracker, weekly job nudges, XP leaderboard, badges, streaks | DAU/MAU >= 30% |
| Revenue | Micro-purchases, Pro Plan, cohort-based flagship course funnel | Rs 10 Cr monthly by Mar '26 |
| Referral | WA invites (unlock rewards), campus challenges, influencer UGC bonuses | Viral Coefficient >= 1.1 |

## Growth Phases (12-Month)

| Phase | Timeline | Focus | Key Tactics |
| --- | --- | --- | --- |
| Phase 1 | 0-3 months | Rapid User Acquisition | Activation loops (invite 10 -> unlock premium), Reactivation of 1.5M dormant records, Campus Ambassador Blitz, Micro-influencer UGC |
| Phase 2 | 3-6 months | Virality + Engagement | Gamification XP ladder + leaderboard, TikTok-style AI Career Tips, WA bot daily feed, CV-scanner -> micro-course upsell |
| Phase 3 | 6-9 months | Monetise + Retain | Pro price tests (Rs 99 vs Rs 499), Scarcity banners, Trigger-based job digests, Community hiring-event funnel |
| Phase 4 | 9-12 months | AI-powered SEO Flywheel | Sitemap-scrape + 1000-article schedule, YouTube SEO, University-placement-portal integration |

## Funnel Maths

Growth math to 10M MAU based on viral coefficient assumptions. k-factor target >= 1.1. CAC heat-map by channel: Meta, Google, WhatsApp, SEO, Ambassadors. Budget split: Paid 35%, Content 25%, Engineering 15%, Community 15%, Ops 10%. Lean 19-person growth pod structure.

# 35. International Expansion Plan

Target Regions: UAE (Dubai, Abu Dhabi), Southeast Asia (Vietnam, Indonesia, Philippines), Africa (Nigeria, Kenya, Egypt)

Why These Markets: Strong international-student inflow + visa uncertainty = higher willingness to pay for credible, fast outcomes.

Motion: University partners, community clubs, Campus Ambassador networks; paid via TikTok/IG/Google; product-led referrals.

| Phase | Timeline | Actions | Metrics |
| --- | --- | --- | --- |
| Pilot | Q2 FY26 | Run pilot in 5 colleges per region via virtual internship programs | Students onboarded, completion rate |
| Localization | Q3 FY26 | Translate AI career planner + WA hiring bot for local languages | Languages launched, local NPS |
| B2B Deals | Q4 FY26 | Close deals with edtechs or gov. skilling orgs for license pilots | Deals closed, revenue |
| Full Launch | FY27 | Full-fledged Beep Global vertical (multi-currency, multi-locale) | ARR, countries active |

## International Pricing

| Product | India Price | International Price |
| --- | --- | --- |
| Micro-Courses | Rs 399-999 | $7-$29 per course; bundles $49-$99 |
| Advanced Tracks | Rs 10K-30K | $199-$499, outcome-linked refund/credit |
| Internship Programs | Rs varies | $399-$999 (includes mentor + placement) |
| Pro Plan | Rs 99/month | $1.99/month (pilot) |
| Recruiter SaaS | Rs 6,800/month | Seat-based + success fee |
| College SaaS | Rs 5-10L ACV | Annual license + outcome playbooks |

# 37. Company Vision & Positioning Statement

## One-line Vision

Build the 'Tier-1 career system' for everyone — a global, AI-powered career OS that helps any student explore, upskill, and get hired fast, regardless of college, background, or country.

## What This Means in Practice

- 1. Figure out their career path (clarity + roadmap) — AI-powered career mapping with daily tasks

- 2. Become job-ready (skills + portfolio + confidence) — Mentor-led + AI-guided programs with projects

- 3. Get real opportunities (internships/jobs + recruiter access) — Direct recruiter network of 8,000+

- 4. Repeat it for life (continuous upskilling as roles change with AI) — Micro-courses + certifications

## Future-Proof Layer (AI Impact)

As AI reduces entry-level roles, students will need: better proof-of-skill (projects, portfolios), better communication + problem-solving, faster iteration and specialization, premium guidance and mentorship. Beep is the platform that provides all of this in a single mobile-first ecosystem, turning 'degree-only' into 'degree + signals + outcomes'.

## Founder Quotes (Fundraise)

Option 1: 'Tier 2/3 students have the same ambition as Tier 1 — only the system doesn't give them the same access. This fundraise is fuel for our mission: build an IIT-like career ecosystem at scale.'

Option 2: 'AI is changing jobs faster than colleges can update curriculum. The opportunity is massive: students will pay for a real edge — skills, mentors, internships, and hiring access.'

Option 3: 'We've already built distribution — millions of students, 800+ college ties, and thousands of recruiters. Now the focus is execution: deepen outcomes, improve conversion, and scale programs.'

# 39. Competitive Landscape

| Category | Players | How Beep Differs |
| --- | --- | --- |
| Job Boards | LinkedIn, Naukri, Apna, FirstNaukri | Focus on early-career, portfolio signals, time-to-shortlist, community-driven acquisition |
| EdTech / Courses | Scaler, PW, Internshala Trainings | Program + placement integration; recruiter access baked in; not just content/courses |
| Campus Hiring (Global) | Handshake | India-focused with deep Tier 2/3 penetration; affordable pricing; local language |
| Recruiting / AI | GetWork.ai, Intervue, Interview.AI, Expertia | Differentiated via student pipeline + learning data + explainable ranking signals |
| Career Prep | PrepInsta, Unstop | Win on integrated program + placement; outcome-tied, not content-only or event-only |
| Networking / Community | Peerlist | Community + learning + hiring unified in one mobile platform; not just networking |

Beep's core edge: We unify community + learning + hiring + college SaaS with a subscription price accessible to the mass market. Most competitors do only one (job board OR courses OR college ERP). Beep creates a closed loop where student engagement data feeds recruiter matching, learning completion signals drive hiring confidence, and college partnerships fuel distribution.

# 38. AI COO System Prompt (Summary)

A comprehensive AI COO system prompt was created with full Beep context to serve as an automated operating system across all 4 verticals. Key components:

- Identity: AI COO for Beep with full knowledge of 4 verticals, team, metrics, problems, and playbooks

- Problems to Solve: Meeting culture, no single source of truth, manual reporting, colliding priorities, CEO time pulled into ops

- Outcomes: Daily CEO dashboard, decision-first cadence, targets + guardrails per vertical, incentive engine, advisor loop

- North Stars: Beep App (Pro Plan MRR), Beep Learn (Cash Collected/Month), BeepHire (MRR), UniBeep (New Colleges/ARR)

- Data Plumbing: Mixpanel/Amplitude -> BigQuery -> Looker/Metabase -> Slack webhooks

- Cadence: Daily async standups + war-room, Weekly WBRs + interlock, Monthly MBR, Quarterly QBR

- Incentives: Variable comp tied to P&L, SPIFFs for 30-day bursts, Golden Beeper recognition, PIP protocol

- Execution Plays: Trial ladders, career roadmap nudges, referral ladders, creator micro-networks for App; Monthly cohorts with anchor recruiters, mentor guild scorecard for Learn; Auto-dialer + Apollo lists for Hire; Placement Pulse roadshows for UniBeep

- Automation: HubSpot CRM, Interakt/Gupshup WA flows, AppsFlyer attribution, Zendesk support, Slack alerts for guardrail breaches

- CEO Time: 40% Revenue, 30% People, 20% Product, 10% Capital

- Advisory: 4 seats (VC/GTM, University/TPO, Recruiter/HR Tech, AI/Product) with 90-day deliverables

--- END OF COMPREHENSIVE DOCUMENT ---

--- END OF DOCUMENT ---