## Weekly Pulse
BEEP — WEEKLY PULSE
April
BEEP LEARN
Metric | Month Target | W1 | W2 | W3 | W4 | % Hit | Status
Cash-in-Bank (₹) | 50,00,000 | 571000 | 500741
New Admissions | 127 | 7 | 18
Net Admissions (after drops) | 112 | 7 | 18
Leads generated |  | 464 | 2003
Qualified Leads |  | 72 | 91
Lead - Qualified |  | 15.5% | 4.5%
Qualified - demo booked |  | 11% | 24%
demo - enrollment |  | 62% | 60%
lead to enrollment |  | 1.08% | 0.9%
Dropout Rate | ≤10% | 0% | 3-5%
Conversion % (Intent→Admit) | ≥25% | 18.42% | 20-22%
Daily Cash-in Avg (₹) | 150000 | 32500 | 71500
Ad Spend (₹) | 10,00,000 | 65757 | 115029
ROAS | ≥2.0x | 1.98 | 4.28
Referral Admissions | Start | 1 | 2
Companies for Placements | 25 | 8 (active) | 8
Team Avg Achievement % | ≥70% | 20-25% | 35-40%
BEEP APP
Metric | Month Target | W1 | W2 | W3 | W4 | % Hit | Status
New Installs | 65000 | 605
New Signups | 50000 | 442
DAU | 10000 | 1301
DAU/MAU % | ≥30% | 4.423%
Pro New Subscribers | 3500 | 37
Pro Plan (₹) | 1000000 | 3219
CPI (₹) | ≤7 | 9.8
CPA per Signup (₹) | Track | 17.21
Cost per pro plan |  | 211
W1 Retention % | ≥25% | 6.45%
W4 Retention % | ≥12%
Content Pieces/Week | 50 | 14/18
Trial→Paid % | ≥7% | 8.371%
UNIBEEP & BEEPHIRE (Frozen — Red flags only)
Vertical | Revenue (₹) | Churn? | Critical Bug? | Pipeline OK? | Team Issue? | Red Flag? | Founder Action?
UniBeep |  | No | No | Yes | No | 🟢 | No
BeepHire |  | No | No | Yes | No | 🟢 | No
COMPANY HEALTH
Metric | Target | Actual | Gap | Status | Owner
Total Revenue MTD (₹) | 4000000 |  |  |  | All
Burn Rate (₹/month) | 4500000 |  |  |  | Finance
Runway (months) | 8 |  |  |  | Saurabh
Bridge Round (₹ Cr) | 1.2 |  |  |  | Saurabh

## Blockers & Actions
KEY BLOCKERS & ACTION ITEMS
TOP BLOCKERS
# | Blocker | Vertical | Impact | Owner | Fix / Next Step | Due | Done?
1 | CRM Migration | Learn | P0 | Kanwaljeet (yogesh) | connect with kanwaljeet and saubhagya | this week | in progress
2 | UGC Agency | Learn | P0 | Aadhya | Aadhya to reach out and onboard an UGC agency for beep app and beep learn creatives | this week | in progress
3 | Revenue Recognition | Learn | P0 | Sales team/Pooja | only 1.27 lacs CIB, Push Pooja for more conversions | this week | in progress
4 | Lead Quality | Learn | P0 | Saubhagya (Saurabh) | Lead qualification issue - never enquired, irrelevant | this week | in progress
5 | No mentor session | Learn | P1 | Sales team | lead qualification issue - no mentor sessions from last 2 days | this week | in progress
6 | Beep Bites | App | P1 | Muskan (Rakhi) | Competitor research; test UGC/trending; Tier 2/3 | this week | not done
7 | Beep Bites - Content Scripting and Analysis | App | P1 | Muskan/Rakhi | research backed scripting for beep bites, collaborate with other creators and influencers for high quality content | 10th april | not done
8 | Web App Tracking (meta) | App | P1 | Gursewak (yogesh) | fix tracking and reporting for webapp related events | this week | not done
9 | User Activity Tracking and Report | App | P1 | Dhruva (aadhya) | Analyze user activity data with Yogesh using Mixpanel, focusing on cohort and variant performance, and share a simplified cohort analysis | this week | not done
10 | Low Quantum of lead | Learn |  | Saubhagya | only 464 generated in 4 days, required quantum 1500+ | this week | in progress
11 | Design and Development Delay | app | P1 | entire product team (yogesh) | delays from the entire product team - push more for developemnt

## Core Problems
CORE PROBLEMS — WHAT MUST BE FIXED
BEEP APP — Core Problems
# | Problem | Severity | Root Cause | Fix | Owner
1 | Content format & UX undecided — production blocked | CRITICAL | 3 options debated but no decision made (Roadmap / COGA / Reels); team brainstorming not deciding | 48hr decision deadline; test with small user set; Yogesh daily product calls | Yogesh / Dhruva
2 | User journey breaks — students get lost | HIGH | No structured flow; videos disconnected; no guided progression through content | Roadmap-driven flow; allow skip but keep structure; invest in Module 1 quality | Dhruva
3 | No retention/engagement data | HIGH | Mixpanel not implemented; no benchmarks; can't measure what's working | Sprint: track events, build funnels, retention cohorts; benchmark 50 competitor apps | Yogesh
4 | Ad CPA spiking — ₹71/signup + ₹696 additional | HIGH | Tier 1 targeting failed; no systematic creative testing; trending formats not leveraged | Research competitors; test UGC, 6767-style; refocus on Tier 2/3 | Muskan / Subagay
5 | Pro Plan conversion inconsistent | MED | Trial funnel not optimized; pricing not A/B tested; unclear Pro value prop | A/B: 3-day ₹9 vs 7-day ₹3; streak vs leaderboard test; Pro sale funnel rework | Yogesh
6 | Content niche undefined — risk of 'just another motivational app' | HIGH | Topics scattered; no content pillars locked; no differentiation strategy | Lock 5-6 pillars (career clarity, skills, industry, earnings, community); roadmap-aligned | Karn / Dhruva
7 | Creator/influencer engine not started | MED | 30-creator target set but no ops, no onboarding, no measurement | Pilot with 5 creators; build onboarding kit; measure performance | Karn
8
BEEP LEARN — Core Problems
# | Problem | Severity | Root Cause | Fix | Owner
1 | Revenue severely behind: ₹7.26L vs ₹17.6L target by 21st | CRITICAL | Low daily cash-in; team not hitting ₹1.5L/day; reliance on month-end push | ₹1.5L/day non-negotiable; daily tracking by 2PM; self-closure pushes | Siddhesh / Rupali
2 | 58% of intent leads lost after mentor sessions | CRITICAL | Mentor session quality — NOT NBFC; poor demo-to-close handoff; no immediate follow-up | Audit mentor sessions; 1-hr follow-up protocol; fix conversion script | Siddhesh
3 | Half the sales team below 45% achievement | HIGH | No individual accountability; unclear daily targets; inconsistent standards | Individual performance plans; daily targets per person; 2-week PIP | Rupali
4 | Net margin still negative (-4%) | HIGH | Direct costs high; ad spend ₹3.3L not yielding proportional returns; ₹30L salary base | Break-even by March; cost audit; increase referral % to lower CAC | Rupali
5 | 28% dropout rate (16 of 57 admissions) | HIGH | Post-enrollment buyer's remorse; quality issues; mentor gaps; communication gaps | Day-7 Save Kit; better onboarding; proactive check-ins; quality docs | Siddhesh
6 | Referral program never launched despite weeks of discussion | HIGH | Talked about every week; no structure; no incentives; no launch date | Build incentive structure; launch Wednesday — NO MORE DELAYS | Siddhesh
7 | Ad ROI declining — spend up, admissions not proportional | MED | ₹3.3L spent; form submissions low; retargeting not optimized | New formats; WhatsApp retargeting; Google My Business; website funnel fixes | Sandeep
8 | Team confidence / internal clarity gap | MED | People unsure if targets are achievable; no shared conviction; morale soft | Transparent targets; daily wins celebration; Rupali more involved daily | Rupali

## FO Role & Beep Weekly
FOUNDER'S OFFICE — ROLE, VISION & BEEP WEEKLY FORMAT
FOUNDER'S OFFICE — What She Owns
# | Responsibility | What It Means (Simply) | Weekly Output | Success =
1 | This Tracker (Single Source of Truth) | Update every Thursday; circulate Friday AM; flag reds on Slack immediately | Updated tracker + 3-line Slack summary | No metric surprise at Monday sync
2 | Daily Learn Revenue Discipline | Check ₹1.5L/day by 2PM with Siddhesh; escalate to Rupali if behind | Daily cash-in confirmed or escalated | Learn hits monthly revenue target
3 | Unblock Beep App Decisions | Facilitate, don't debate; set 48hr deadlines; ensure Yogesh/Dhruva decide | Key decisions documented + shipped | App team shipping, not meeting
4 | Founder Sync Prep | Prepare pre-read by Sunday night using this tracker; run Monday sync | Agenda + pre-read circulated Sunday PM | 60-min sync = 5+ decisions made
5 | Fundraise Support | Data room updated weekly; investor update prepped for Saurabh | Data room current; 1 update email drafted | Bridge round closes on schedule
6 | Frozen Verticals Health Check | 30-min weekly with Aniket (UniBeep) & Rakhi (BeepHire); fill pulse row | Pulse filled in Sheet 1; red flags escalated | No silent degradation
7 | Action Item Follow-Through | Every action from Monday sync tracked; chase owners; report closure rate | ≥80% actions closed by next Monday | Accountability is real, not a slide
8 | Culture & Comms Pulse | Monthly AMA; team morale check; post-mortems within 48hrs of failures | Monthly pulse check; issues flagged early | No key-person attrition surprises
FO'S OWN ACTIONS THIS WEEK
# | Initiative | Why | By When | Done?
1 | Update this tracker with latest numbers | Founders need current data for Monday sync | Thursday
2 | Check Learn daily cash-in with Siddhesh (daily 2PM) | Revenue is existential; daily tracking prevents month-end panic | Daily
3 | Push content format decision to closure (App) | Every day of indecision = lost users; blocked production | Wednesday
4 | Ensure referral program launches (Learn) | Lowest-CAC channel; weeks delayed already | Wednesday
5 | Compile 50-app competitive research (App) | Team needs data for format/content decisions | Friday
6 | Prep Monday founder sync agenda + pre-read | Structured sync = decisions, not status updates | Sunday PM
7 | 30-min check-in: Aniket (UniBeep) + Rakhi (BeepHire) | Confirm self-running; catch red flags | This week
8 | Update fundraise data room for Saurabh | Bridge round urgency — data must be current | Friday
0 of 8 done
BEEP WEEKLY — Monday Founder Sync (60 min)
# | Section | Time | Content | Decision Needed?
1 | Reality Check: Key Metrics | 10 min | Learn: cash-in, admissions, conversion, margin App: DAU, signups, Pro MRR, CPA, retention Company: total revenue, burn, runway | Flag anything ≥15% off target
2 | WoW Trends | 5 min | Are metrics improving week-on-week? Will we hit month-end at this pace? | Course correct if trajectory off
3 | Beep App Deep Dive | 10 min | Top blocker + experiment results + content progress Action items from last week — done or not? | 1-2 decisions from founders
4 | Beep Learn Deep Dive | 10 min | Revenue pace vs daily target + funnel + team performance Action items from last week — done or not? | 1-2 decisions from founders
5 | UniBeep & BeepHire Pulse | 5 min | Quick: any red flags? (from frozen tracker) Only discuss if red flag exists | Only if red flags
6 | Vision & Direction Check | 10 min | Thesis check: are we building Career OS or drifting? Fundraise update + hiring gaps Any strategic pivots needed? | Strategic decisions
7 | Top 3 Critical Problems | 5 min | What could break us if not fixed? What changed since last week? | Assign owners + deadlines
8 | Decision Log & Actions | 5 min | Document every decision; assign actions; read back | Confirm all decisions

## Vision & Thesis
ARE WE GOING IN THE RIGHT DIRECTION?
THESIS CHECK (Update Monthly)
# | Our Thesis | What We Said | Reality Right Now | On Track? | Course Correction
1 | Career OS for Tier 2/3 | AI career platform replacing Tier 1 ecosystem for masses | App exists but UX broken; content not shipping; no differentiation yet | 🟡 | Finalize format THIS WEEK; roadmap = core product; ship outcomes
2 | Learn = Cash Engine | Beep Learn funds the rest; largest revenue vertical | Largest vertical but behind targets; -4% margin; high dropout | 🟡 | Break-even March; fix mentor funnel; launch referrals; daily discipline
3 | Multi-Sided Network | Students + recruiters + colleges reinforce each other | Verticals in silos; UniBeep & BeepHire frozen; no synergy active | 🔴 | Accept frozen for now; plan Q2 re-integration
4 | Outcome-Driven (Placements) | Revenue tied to actual outcomes; 5,000 placements FY26 | 550 FY25; tracking weak; placement proof system doesn't exist | 🟡 | Build student ID tracking; placement proof; count only measurable
5 | Data Flywheel + AI Edge | 4M profiles; signal-driven AI matching | Mixpanel not implemented; AI scoring errors; data plumbing broken | 🔴 | Mixpanel sprint; fix AI quality; BigQuery pipeline
6 | Capital Efficient | Burn ≤₹45L; bridge + seed to extend runway | Salary ₹30L alone; total burn ~₹40-50L; bridge ₹1.2Cr critical | 🟡 | Cost cuts; Learn break-even; fundraise with urgency
7 | 5,000 Placed FY26 | Measurable impact across verticals | Too early; infrastructure for tracking doesn't exist yet | 🟡 | Build tracking now; set Q1/Q2 intermediate milestones
TOP 5 MOST CRITICAL PROBLEMS (Updated Weekly)
Rank | Problem | Why It's Critical | Owner | What We're Doing | Deadline
#1 | Cash crunch — Learn behind + high burn | ₹30L salary; Learn at ₹7.26L vs ₹17.6L; March must show positive | Saurabh + Rupali | ₹1.5L/day; cost audit; bridge acceleration | March end
#2 | App content/UX indecision | Every day without decision = lost users + wasted team time | Yogesh + Dhruva | Decide this week; daily calls; test not debate | This week
#3 | Learn team underperformance | 50% below 45%; targets structurally impossible if half team drags | Rupali | Individual plans; daily accountability; PIP in 2wks | 2 weeks
#4 | Bridge round not closed | Runway depends on ₹1.2Cr; delay = less negotiating power | Saurabh | Data room live; weekly outreach; advisory leverage | April
#5 | No data infrastructure | Can't measure retention; decisions on gut not data | Yogesh | Mixpanel sprint; events + funnels + cohorts | 3 weeks
COMPANY GOALS THIS MONTH
# | Goal | Target | Actual | Status | Notes
1 | Total Revenue (Cash-in-Bank) | ₹40-45L |  |  | App + Learn primarily
2 | Burn Rate | ≤₹45L |  |  | Salary ₹30L + ops + ads
3 | Runway | ≥8 months |  |  | Depends on bridge
4 | Bridge Round | ₹1.2 Cr |  |  | Data room ready
5 | Learn Break-Even | Net positive |  |  | Currently -4%
6 | App Content Launch | Format decided + Module 1 |  |  | Currently blocked
7 | Referral Program (Learn) | Launched + tracking |  |  | Weeks delayed
8 | Team Performance | ≥70% avg achievement |  |  | Currently ~45%